Chicken Coop Materials Summary

French cottage-style coop + walk-in run · 5'×10' coop, 16'×4' run · for 15 hens

Reflects v11 plan set (5'×10' coop) · supersedes all prior versions

Budget at a glance

Total estimated cost for the full coop + run build is approximately $4,240 (v11), broken down across 12 categories. Prices are Home Depot national-chain estimates as of May 2026; verify locally before purchase. SLC area pricing is generally consistent with national averages. Note: the authoritative source for all quantities and costs is coop-materials-list.xlsx — if any figure here disagrees, trust the spreadsheet.

This budget excludes the salvaged transom and slider windows you already own. Tools are included as line items, but several at $0 reflect tools assumed already owned (circular saw, drill/driver).

Note: this total is higher than the original $3,300-$3,500 target because four rounds of plan review identified structural and predator-proofing improvements (hybrid foundation for kid-safety, additional hardware-cloth screws, knee bracing, etc.). See CHANGES-v10-to-v11.md for the full revision history.

Cost by category

| Category | Subtotal | % of project |
| --- | --- | --- |
| Run Structure | $854 | 20.0% |
| Foundation & Floor Framing | $688 | 16.1% |
| Siding & Trim | $583 | 13.6% |
| Doors, Windows & Hardware | $454 | 10.6% |
| Hardware Cloth & Predator-Proofing | $383 | 9.0% |
| Roof Sheathing & Roofing | $357 | 8.4% |
| Wall Framing | $286 | 6.7% |
| Roof Framing | $182 | 4.3% |
| Misc Hardware & Fasteners | $135 | 2.9% |
| Paint & Finish | $123 | 3.2% |
| Interior Fixtures | $124 | 2.9% |
| Tools (verify before buying) | $102 | 2.4% |
| TOTAL | $4,240 | 100% |

Recommended buying sequence

Don't buy everything at once. Materials get damaged, lost, or warped when stored too long. Stage purchases to match the build phases.

Phase 1 — Foundation (week 1)

Concrete and forms: 14 bags Quikrete Fast-Setting (50-lb, no-mix sonotube formulation), 8 × 10" Sonotube forms, 8 EPB44HDG brackets, EPB post fasteners: (8) 0.162×3½ nails or (8) SD10 1½" screws per bracket

Run mid-span hardware: 4 deck blocks, 4 × 18" rebar pins, 2 bags crushed gravel

Floor framing lumber: all PT lumber for floor (4×4 posts, 2×10 rim joists, 2×6 end and floor joists)

Hardware: Simpson LUS26 joist hangers + hanger nails

Decking: ¾" PT plywood (2 sheets)

Foundation must cure before walls go up, and PT lumber is the most weather-tolerant if you have to store it briefly outside. The 8 concrete footers (4 coop + 4 run corners) pour in one day; the 4 mid-span deck blocks set the next day.

Building in phases (coop first, run later)

If you're building the coop now and the run later — a common approach — defer the run foundation work to whenever you start the run. For Phase 1 in coop-first mode, pour only the 4 coop footers (6 bags Quikrete, 4 sonotubes, 4 EPB44HDG brackets, 4 × 20" coop posts). Drive 4 stakes at the run corner positions to lock in the run geometry while you build the coop. When you're ready to build the run, the run foundation work becomes a separate 1-2 day phase using the same procedure: 4 more footer holes, 6 more bags of concrete, 4 more EPB44HDG brackets, plus the 4 mid-span deck blocks and rebar pins.

Materials to defer in coop-first mode: U01 (run posts, all 8), U02 (4 deck blocks), U03 (gravel for blocks), U11 (rebar pins), U13-U16 (run-corner concrete/sonotubes/brackets/bolts). You'll order these months later when you're ready to build the run.

Phase 2 — Wall and roof framing (week 2-3)

Wall studs and plates: all 2×4 SPF and 2×6 SPF for walls and top plates

Roof framing: 2×6 rafters, 2×8 ridge, 18 Simpson H1 hurricane ties

Sheathing: ½" OSB sheets (4 for coop roof, 3 for run roof)

SPF lumber is more sensitive to weather than PT; minimize storage time. Buy this batch when ready to start framing.

Phase 3 — Weatherproofing (week 3-4)

Roofing materials: 30# felt, 4 bundles shingles, 1 bundle ridge cap, drip edge, flashing, roofing nails, roofing cement

Siding: board-and-batten lumber (1×8 boards, 1×3 battens), trim boards, 1×6 fascia

Caulk and sealants: exterior silicone caulk, roofing cement

Get the roof on quickly to weatherproof. Siding can wait briefly under tarps if needed.

Phase 4 — Doors, windows, finish (week 4-5)

Hardware: all hinges, latches, hooks, hardware cloth (1 × 100' roll + 1 × 25' backup roll)

Hardware cloth fasteners: poultry staples + 300 self-tapping screws with neoprene washers

Interior fixtures: plywood for shelf/cabinet/nest box, rolled linoleum, astroturf nest pads

Paint and primer: exterior paint, primer, trim accent color, brushes/rollers

Dutch door astragal trim (1×2 weatherstripped strip)

Phase 5 — Run construction (week 5-6)

Run-specific lumber: 4×4 PT posts (8), 2×6 PT top rails (5), 2×4 PT bottom rails (5), 2×3 SPF studs, 1×6 PT skirt boards (5)

Run roof: 2×6 SPF rafters, OSB sheathing, share shingles + felt from Phase 3 order if any leftover

Structural fasteners: 150 × #10 × 3½" structural wood screws, 8 carriage bolts + washers

Diagonal bracing: 3 × 2×4 SPF for 8 knee braces

Run can be built in parallel with coop finishing once the run foundation is in. Some items (hardware cloth, structural screws) overlap with the coop order — buy once.

Where to source

Home Depot / Lowe's (~85% of budget)

Most lumber, hardware, plywood, OSB, fasteners, paint, and shingles will come from a national chain. Both stores carry essentially identical product lines at this scale, and prices are usually within a few percent. Pick whichever is more convenient.

Pro tip: sign up for the contractor account (free, both stores) for paper-account billing and bulk discounts. Also check the "clearance lumber" rack — slightly imperfect boards are fine for chicken coop work and often run 25-50% off.

Specialty / online (~10%)

Astroturf mats for nest boxes — Amazon

Decorative cupola finial — Etsy or Wayfair (or fabricate from scrap)

Auto chicken-door opener if going automatic — Amazon, ChickenGuard brand

Foam padding for egg trays — craft store or Amazon

Simpson structural connectors (EPB44HDG, LUS26, H1) — Home Depot carries them, but a specialty supplier may have better prices in bulk

Local lumber yard (~5%)

For specific structural lumber (PT 2×10s especially), a local yard often has better quality and pricing than chains. Worth a comparison call. Check Sutherlands or any SLC-area independent lumber yard.

Salvage (already acquired, excluded from budget)

72" × 12" transom window — owned

Two 24" × 24" residential slider windows — owned

If you want to source more from salvage to reduce cost: SLC Habitat for Humanity ReStore often carries PT lumber, plywood, trim, and hardware at 30-60% off retail. Worth a visit before placing the Phase 1 lumber order.

Where to save (or splurge)

Easy savings

These changes don't compromise the structural or kid-safety improvements identified during plan review:

Pre-fab Dutch door → build your own: pre-fab cottage Dutch doors run $400-600; building from 1×6 T&G with hinges costs $50-75 (already assumed in BOM)

Stud-grade vs premium SPF: stud-grade 2×4s are 15-25% cheaper and structurally identical for this scale

Asphalt shingles vs metal roof: architectural asphalt is ⅓ the cost of metal and lasts 25-30 years

Used lumber from Habitat ReStore: 30-60% off, especially for non-PT framing lumber

If you own a circular saw, drill, post-hole digger, and level: subtract ~$80 from the tools line

Source the hardware cloth from farm supply (IFA in Utah) rather than HD — often 10-15% cheaper for 100' rolls

Do NOT save on these

These were specifically identified during plan review as kid-safety or structural items that should not be downgraded:

Run corner concrete footers + EPB44HDG brackets (the whole reason the run is safe for kids)

150 × #10 × 3½" structural wood screws (rail-to-post + knee brace attachment)

300 × self-tapping screws + neoprene washers for hardware cloth (predator-resistant attachment at all high-stress edges)

Galvanized hardware (hinges, latches, gate hardware) — non-galvanized rusts within a year outdoors

PT lumber wherever the BOM calls for it — using SPF in ground-contact zones leads to rot in 5-8 years

Realistic budget scenarios

| Scenario | Total | Saves |
| --- | --- | --- |
| Baseline (May 2026 prices, BOM as-spec) | $4,240 | — |
| With already-owned tools | $4,169 | −$102 |
| With clearance lumber + IFA hardware cloth | $3,991 | −$280 |
| All savings applied (excl. structural compromises) | $3,891 | −$380 |

Key design decisions (for future-you or anyone helping you)

What the plans include and why

Hybrid run foundation: 4 corners on concrete footers + EPB44HDG brackets, 4 mid-span on deck blocks with rebar pins. Chosen specifically to handle kid-loads (children climbing, hanging, running into walls). Concrete corners provide positive mechanical anchorage where lateral and torsional loads concentrate.

No wall insulation: SLC climate with cold-hardy breeds doesn't need it. Insulation traps moisture and causes frostbite (the actual chicken-killer in winter is moisture, not cold). Ventilation matters more — hence the cupola + gable vents + slider windows.

Rolled linoleum floor running 2-3" up walls as cove base: fewer seams = easier cleanup, less mite/debris harborage than tile squares.

Cupola with louvered sides: passive moisture exhaust at the peak. Hot moist air rises out of the coop overnight.

8:12 roof pitch: French cottage aesthetic per spec; also sheds SLC snow well.

Dutch door on south wall: classic cottage element + allows ventilation when top half is open in summer.

Run roof slopes 3:12 to north: keeps rainwater off the south yard, drains to fence buffer instead.

Field decisions still pending

These aren't bugs in the plan — they're items where actual on-site measurements will determine the final detail:

Run-roof-to-coop-wall flashing: install Z-flashing or step flashing where the run roof tucks under the coop's west wall siding. Exact dimensions depend on measured fit.

Run post final cut lengths: cut conservatively long, then trim each post after measuring its actual bracket or block elevation post-pour.

Optional foam-board ceiling insulation: ~$30 in materials, optional add for cold winters. Trade-off: small thermal benefit vs. risk of moisture/mice. Owner's call after first winter.